## Burn Down Chart
Project Title: Milestone 6 Release #: 6.0 Sprint #: 6
| User Story ID | Log Type | User Story | Task | Assigned To | Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Amounts Left
| 1 | Back Log | As a programmer I would like to see the program updated and maintained | make updates to maintain code with suggested updates from last milestone and from peer code reviews | All | 10 | 2 | 2 | 2 | 2 | 2 | 0 | 0
| 2 | Product | As a programmer I would like to implement Leverage IoC dependency injection | Example would be to inject a Logger Service into at least one Controller |  | 8 | 2 |  | 2 |  | 2 | 2
| 3 | Product | As a programmer I would like to implement Leverage HTTP Request filter | Example would be to perform page security |  | 8 | 2 |  | 2 |  | 2 | 2
| Ideal - Remaining efforts in uninterrupted working hours |  |  |  |  | 26 | 22.2857 | 18.5714 | 14.8571 | 11.1429 | 7.4286 | 3.7143 | -4.4409e-15
| Actual - Remaining efforts in uninterrupted working hours |  |  |  |  | 26 | 20 | 17 | 13 | 10 | 7 | 2 | 0